## Project tracker
Project tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2024-02-25 | 2024-04-25 | 210 | 60 | 2024-02-25 | 2024-04-30 | 300 | 65
Project 2 | Category 2 | Employee 4 | 2024-03-20 | 2024-04-20 | 400 | 30 | 2024-03-20 | 2024-04-23 | 390 | 33
Project 3 | Category 1 | Employee 2 | 2024-01-21 | 2024-03-21 | 500 | 60 | 2024-01-21 | 2024-04-03 | 500 | 72
Project 4 | Category 2 | Employee 3 | 2024-01-31 | 2024-02-10 | 250 | 10 | 2024-01-31 | 2024-02-19 | 276 | 19
Project 5 | Category 3 | Employee 2 | 2024-01-31 | 2024-03-11 | 300 | 41 | 2024-01-31 | 2024-03-17 | 310 | 47
Project 6 | Category 4 | Employee 4 | 2024-03-01 | 2024-03-11 | 500 | 10 | 2024-03-01 | 2024-03-16 | 510 | 15
Project 7 | Category 5 | Employee 1 | 2024-03-17 | 2024-04-10 | 750 | 23 | 2024-03-17 | 2024-04-15 | 790 | 28
Project 8 | Category 2 | Employee 1 | 2024-03-22 | 2024-04-30 | 450 | 38 | 2024-03-16 | 2024-04-25 | 430 | 39
Project 9 | Category 4 | Employee 1 | 2024-01-26 | 2024-02-15 | 250 | 19 | 2024-01-31 | 2024-02-10 | 200 | 10
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS